## Summary
FRIEND OR PHISH? — CYBERDESK ASSET INVENTORY
Production tracker for assets, animation behaviors, and next-frame requirements.
Metric | Value | Notes
Unique asset/component rows | 94 | Each row is one tracked asset or asset family.
Total asset quantity target | 357 | Quantity sums the planned icons, variants, and asset families listed in Qty.
Core rows | 72 | Recommended for the initial playable prototype.
Later rows | 22 | Polish or expansion items.
Completion status | Complete (94/94 rows) | All rows implemented and checked; see Asset Inventory columns K-M and REPORT.md for caveats and approvals.
Category totals
Category | Rows | Qty Total
Boot Sequence | 13 | 18
Desktop | 11 | 14
Icons | 5 | 64
Window UI | 10 | 40
Mail | 10 | 59
Browser | 10 | 18
Link Inspector | 6 | 11
Security Center | 6 | 15
Files | 6 | 19
Progression & Extras | 17 | 99

## Asset Inventory
No. | Category | Asset Name | Qty | Format / Type | Visual Description | Animation / Behavior | Next Frame / Animation Extra | Priority | Status | Delivered files (summary) | Component(s) | Verified by
1 | Boot Sequence | CyberDesk logo | 1 | SVG/PNG | Pixel CRT monitor above bold retro lettering. | Logo powers on; screen glows. | Frame 1: screen dark → Frame 2: blue screen → Frame 3: logo illuminates. | Core | Complete | 8 files, e.g. boot/logo-frame1.svg | see manifest.json | Contact sheet review + asset loads without errors in app
2 | Boot Sequence | System emblem | 1 | SVG/PNG | Small pixel-art system badge. | Brief glow pulse. | Frame 1: normal → Frame 2: bright highlight → Frame 3: normal. | Core | Complete | 4 files, e.g. boot/emblem.svg | see manifest.json | Contact sheet review + asset loads without errors in app
3 | Boot Sequence | Boot background | 1 | CSS/PNG | Black CRT-style screen with subtle scanlines. | Very subtle scanline movement. | Frame 1: dark screen → Frame 2: faint horizontal lines → Frame 3: steady screen. | Core | Complete | 2 files, e.g. boot/boot-bg.png | see manifest.json | Contact sheet review + asset loads without errors in app
4 | Boot Sequence | Startup diagnostics | 1 | Text/UI | Green monospaced diagnostic lines. | Lines appear one by one. | Frame 1: cursor → Frame 2: first line → Frame 3: next line → Frame 4: all checks complete. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/Boot.jsx#BootScreen | sweep 01-boot
5 | Boot Sequence | Loading bar | 1 | CSS | Classic gray-bordered progress bar. | Fill moves left to right. | Frame 1: 0% → Frame 2: 25% → Frame 3: 60% → Frame 4: 100%. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/Boot.jsx; src/cyberdesk/styles/anim.css | sweep 01-boot
6 | Boot Sequence | Blinking cursor | 1 | CSS | Small green rectangular terminal cursor. | Alternates visible and hidden. | Frame 1: visible → Frame 2: hidden → repeat. | Core | Complete | No file (CSS / React component) | src/cyberdesk/styles/anim.css (cd-blink) | sweep 01-boot
7 | Boot Sequence | Disk-access indicator | 1 | SVG/CSS | Tiny disk or drive activity light. | Flickers during simulated access. | Frame 1: off → Frame 2: lit → Frame 3: off. | Core | Complete | 4 files, e.g. boot/disk-led-off.svg | see manifest.json | Contact sheet review + asset loads without errors in app
8 | Boot Sequence | System initialization icons | 6 | SVG/PNG | Small memory, storage, network, audio, display, and security icons. | Each lights up after its check. | Frame 1: gray icon → Frame 2: colored icon → Frame 3: check mark. | Core | Complete | 36 files, e.g. boot/init/memory-gray.svg | see manifest.json | Contact sheet review + asset loads without errors in app
9 | Boot Sequence | Startup warning screen | 1 | React/CSS | Classic warning dialog on black or gray background. | Dialog appears with a small pop-in. | Frame 1: empty screen → Frame 2: dialog appears → Frame 3: button becomes active. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/Boot.jsx#WarningScreen | sweep 00-warning
10 | Boot Sequence | Boot completion transition | 1 | CSS/Motion | Desktop fades in after startup. | Short fade and optional subtle flicker. | Frame 1: black → Frame 2: wallpaper faint → Frame 3: full desktop. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/Boot.jsx; src/cyberdesk/styles/anim.css | flow/sweep: boot -> desktop reveal
11 | Boot Sequence | Shutdown screen | 1 | CSS/PNG | Black screen with centered shutdown text and logo. | Text fades; logo dims. | Frame 1: desktop fades → Frame 2: shutdown text → Frame 3: black screen. | Core | Complete | 2 files, e.g. boot/shutdown.svg | see manifest.json | Contact sheet review + asset loads without errors in app
12 | Boot Sequence | CRT scanline overlay | 1 | CSS | Subtle horizontal scanlines. | Slow, nearly imperceptible drift. | Frame 1: lines at position A → Frame 2: lines at position B → loop. | Core | Complete | 1 files, e.g. boot/scanlines-tile.png | see manifest.json | Contact sheet review + asset loads without errors in app
13 | Boot Sequence | Screen flicker overlay | 1 | CSS | Very brief low-intensity brightness variation. | One short flicker at boot only. | Frame 1: normal → Frame 2: slightly dim → Frame 3: normal. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/Boot.jsx#CrtOverlay; src/cyberdesk/styles/anim.css (cd-flicker) | CSS present; reduced-motion disables NOTE: visual intensity is a tunable CSS value; disabled under reduced motion.
14 | Desktop | Main desktop wallpaper | 1 | PNG/WebP | Retro pixel-art landscape or classic teal desktop. | Static; optional subtle ambience only. | Frame 1: base wallpaper → Frame 2: optional subtle ambient light variation. | Core | Complete | 3 files, e.g. wallpapers/landscape.png | see manifest.json | Contact sheet review + asset loads without errors in app
15 | Desktop | Alternate wallpapers | 3 | PNG/WebP | Campus, nighttime city, and retro computer-room themes. | Static selectable backgrounds. | Frame 1: wallpaper A → user selects B → smooth crossfade to B. | Later | Complete | 9 files, e.g. wallpapers/campus.png | see manifest.json | Contact sheet review + asset loads without errors in app
16 | Desktop | Taskbar | 1 | React/CSS | Classic gray taskbar with Start, open apps, and system tray. | Open apps gain taskbar buttons; active app highlighted. | Frame 1: inactive button → Frame 2: pressed/active button. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/Taskbar.jsx | sweep 02-desktop
17 | Desktop | Start menu | 1 | React/CSS | Rectangular gray menu with app icons and text. | Opens upward; selected row highlights. | Frame 1: closed → Frame 2: opening → Frame 3: open; hover row changes highlight. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/Taskbar.jsx#StartMenu | sweep 03-startmenu
18 | Desktop | System tray | 1 | React/CSS | Small network, volume, clock, and security indicators. | Status icon changes with simulation events. | Frame 1: normal network → Frame 2: disconnected icon when event fires. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/Taskbar.jsx#Tray | sweep 02-desktop
19 | Desktop | Clock and calendar | 1 | React/CSS | Classic digital clock and small calendar panel. | Clock updates; calendar opens on click. | Frame 1: clock visible → Frame 2: calendar popup opens → Frame 3: closes. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/Taskbar.jsx#Clock,Calendar | sweep 04-calendar
20 | Desktop | Desktop icon grid | 1 | React/CSS | Aligned desktop shortcuts with labels. | Selection rectangle and hover states. | Frame 1: idle icon → Frame 2: selected highlight → Frame 3: double-click opens app. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/Desktop.jsx | sweep 02-desktop
21 | Desktop | Desktop context menu | 1 | React/CSS | Gray right-click menu with compact options. | Appears at pointer; hover row highlights. | Frame 1: hidden → Frame 2: menu appears → Frame 3: selected action. | Later | Complete | No file (CSS / React component) | src/cyberdesk/os/Desktop.jsx#ContextMenu | sweep 05-desktop-ctx
22 | Desktop | Shortcut arrow overlay | 1 | SVG | Small arrow overlay at icon corner. | Static. | Frame 1: icon only → Frame 2: shortcut arrow overlaid. | Later | Complete | 14 files, e.g. icons/overlay/shortcut.svg | see manifest.json | Contact sheet review + asset loads without errors in app
23 | Desktop | Recycle Bin empty/full | 2 | SVG/PNG | Classic pixel bin in empty and full states. | Changes state when simulated files are deleted/restored. | Frame 1: empty bin → Frame 2: full bin after delete → Frame 3: empty after emptying. | Later | Complete | 4 files, e.g. desktop/recycle-empty.svg | see manifest.json | Contact sheet review + asset loads without errors in app
24 | Desktop | Shutdown confirmation dialog | 1 | React/CSS | Classic dialog with Yes and No buttons. | Pop-in and button press states. | Frame 1: dialog closed → Frame 2: dialog open → Frame 3: selected button pressed. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/ui.jsx#DialogView | sweep2 s2-18-shutdown-dialog
25 | Icons | System icons | 18 | SVG/PNG | Classic small pixel icons for computer, network, drives, settings, help, printer, search, control panel, etc. | Hover highlight; click/selection states. | Frame 1: normal → Frame 2: hover highlight → Frame 3: selected. | Later | Complete | 36 files, e.g. icons/system/my_computer.svg | see manifest.json | Contact sheet review + asset loads without errors in app
26 | Icons | Application icons | 12 | SVG/PNG | Mail, Browser, Security Center, Files, Terminal, Notes, Calculator, Downloads, Help, Settings, etc. | Unread/alert badges may pulse once. | Frame 1: normal icon → Frame 2: badge appears → Frame 3: badge settles. | Core | Complete | 24 files, e.g. icons/app/mail.svg | see manifest.json | Contact sheet review + asset loads without errors in app
27 | Icons | File-type icons | 12 | SVG/PNG | Folder, text, PDF, image, spreadsheet, archive, executable, shortcut, unknown file, attachment, quarantined file. | Selected file receives a highlight; quarantined file shows overlay. | Frame 1: normal → Frame 2: selected → Frame 3: warning overlay if applicable. | Core | Complete | 38 files, e.g. icons/filetype/folder.svg | see manifest.json | Contact sheet review + asset loads without errors in app
28 | Icons | Status/security icons | 12 | SVG/PNG | Information, warning, error, success, suspicious, verified, blocked, unknown, shield, evidence found. | Use static state variants; optional short pulse on new event. | Frame 1: neutral → Frame 2: state icon changes to warning/success → Frame 3: settles. | Core | Complete | 24 files, e.g. icons/status/info.svg | see manifest.json | Contact sheet review + asset loads without errors in app
29 | Icons | Cursor pack | 10 | CUR/PNG/CSS | Arrow, link hand, text I-beam, busy, forbidden, resize, precision cursors. | Busy cursor cycles; resize cursor follows edge direction. | Frame 1: pointer → Frame 2: busy animation or resize state → Frame 3: default. | Later | Complete | 26 files, e.g. cursors/arrow.svg | see manifest.json | Contact sheet review + asset loads without errors in app
30 | Window UI | Active window frame | 1 | React/CSS | Gray beveled frame with blue title bar. | Changes focus when clicked. | Frame 1: inactive gray title → Frame 2: active blue title. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/AppWindow.jsx; src/cyberdesk/styles/os.css | all screenshots
31 | Window UI | Inactive window frame | 1 | React/CSS | Gray frame with muted title bar. | Becomes active on focus. | Frame 1: inactive → Frame 2: active when selected. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/AppWindow.jsx (.inactive) | sweep2 (stacked windows)
32 | Window UI | Title bar and app icon slot | 1 | React/CSS | App icon and title plus window controls. | Title bar drag moves window. | Frame 1: window position A → Frame 2: window position B while dragging. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/AppWindow.jsx | all screenshots
33 | Window UI | Minimize/maximize/restore/close controls | 4 | CSS/SVG | Classic small beveled control buttons. | Pressed state; window minimizes, maximizes, restores, or closes. | Frame 1: raised button → Frame 2: pressed button → Frame 3: resulting window state. | Core | Complete | 8 files, e.g. window/glyph-minimize.svg | see manifest.json | Contact sheet review + asset loads without errors in app
34 | Window UI | Resize handles | 8 | CSS | Invisible or subtle handles on edges and corners. | Window follows pointer while resizing. | Frame 1: default size → Frame 2: drag edge → Frame 3: resized window. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/AppWindow.jsx (8 handles) | CSS/handles present; drag-resize not pixel-tested
35 | Window UI | Window shadow | 2 | CSS | Subtle shadow for layered windows. | Follows active window and stacking order. | Frame 1: behind window → Frame 2: shadow emphasizes focused window. | Core | Complete | No file (CSS / React component) | src/cyberdesk/styles/os.css (.win box-shadow) | all screenshots
36 | Window UI | Buttons and inputs | 12 | React/CSS | Raised/pressed/disabled buttons, inputs, checkboxes, radio buttons, dropdowns. | Hover, focus, pressed, disabled, and checked states. | Frame 1: normal → Frame 2: hover/focus → Frame 3: pressed/selected. | Core | Complete | 12 files, e.g. window/glyph-check.svg | see manifest.json | Contact sheet review + asset loads without errors in app
37 | Window UI | Scrollbars and tabs | 4 | React/CSS | Classic narrow scrollbars and raised tabs. | Thumb moves with content; active tab changes. | Frame 1: inactive tab → Frame 2: selected tab; scrollbar thumb moves. | Core | Complete | 8 files, e.g. window/glyph-arrow-up.svg | see manifest.json | Contact sheet review + asset loads without errors in app
38 | Window UI | Tooltips and context menus | 2 | React/CSS | Small pale tooltip and compact gray menu. | Tooltip appears after delay; menu appears on right-click. | Frame 1: hidden → Frame 2: visible → Frame 3: dismiss. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/ui.jsx#Tip,ContextMenu | flow 11-linkmenu, sweep 05
39 | Window UI | Dialog family | 5 | React/CSS | Information, warning, error, confirmation, file-properties dialogs. | Pop-in, button press, and dismissal. | Frame 1: hidden → Frame 2: appears → Frame 3: action selected → Frame 4: closes. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/ui.jsx#DialogView | flow 15,17; sweep2 s2-01,05,18
40 | Mail | Mail app window | 1 | React/CSS | Classic inbox with folder sidebar, message list, reading pane. | Window open/close and pane selection. | Frame 1: desktop icon → Frame 2: window opens → Frame 3: inbox visible. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/Mail.jsx | flow 10; sweep2
41 | Mail | Inbox/message rows | 1 | React/CSS | Rows with sender, subject, date, and read status. | Unread becomes read when opened. | Frame 1: bold unread row → Frame 2: row opened → Frame 3: regular read row. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/Mail.jsx | flow 10; sweep2 s2-04
42 | Mail | Sender avatars | 20 | PNG/SVG | Pixel portraits, initials, or fictional organization marks. | Static; optional small online indicator for known contacts. | Frame 1: avatar → Frame 2: optional presence dot changes. | Core | Complete | 41 files, e.g. mail/avatars/maya-okafor.svg | see manifest.json | Contact sheet review + asset loads without errors in app
43 | Mail | Email signature templates | 8 | HTML/Data | Simple fictional company or university signatures. | Static content within email. | Frame 1: signature collapsed/hidden → Frame 2: full signature visible. | Core | Complete | 1 files, e.g. data/signatures.json | see manifest.json | Contact sheet review + asset loads without errors in app
44 | Mail | Email body layouts | 6 | HTML/Data | Readable message layouts with links, signatures, and optional banners. | Links show destination on hover. | Frame 1: link at rest → Frame 2: hover reveals actual destination in status bar. | Core | Complete | 1 files, e.g. data/layouts.json | see manifest.json | Contact sheet review + asset loads without errors in app
45 | Mail | Attachment icon family | 10 | SVG/PNG | PDF, document, image, archive, spreadsheet, executable, and unknown file icons. | Download/blocked/quarantined overlays. | Frame 1: normal file → Frame 2: download progress → Frame 3: complete or blocked state. | Core | Complete | 32 files, e.g. icons/overlay/shortcut.svg | see manifest.json | Contact sheet review + asset loads without errors in app
46 | Mail | Mail toolbar | 10 | SVG/React | Reply, forward, delete, archive, compose, search, report controls. | Buttons depress and perform action. | Frame 1: raised → Frame 2: pressed → Frame 3: action result. | Core | Complete | 20 files, e.g. toolbar/reply.svg | see manifest.json | Contact sheet review + asset loads without errors in app
47 | Mail | Link context menu | 1 | React/CSS | Open, Copy Link Address, Inspect Destination, Cancel. | Appears at pointer and closes after selection. | Frame 1: hidden → Frame 2: menu open → Frame 3: chosen action. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/Mail.jsx | flow 11-linkmenu
48 | Mail | New mail notification | 1 | React/CSS | Small envelope pop-up with sender and subject preview. | Slides in, remains briefly, then dismisses. | Frame 1: hidden → Frame 2: slide in → Frame 3: visible → Frame 4: fade out. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/Notifications.jsx#Toasts | sweep2 s2-04 (Sam Rivera toast)
49 | Mail | Email search/filter | 1 | React/CSS | Search field and filter controls. | Results update as user types or submits. | Frame 1: empty → Frame 2: query entered → Frame 3: filtered inbox. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/Mail.jsx | sweep2 s2-04 (filter)
50 | Browser | Browser window and toolbar | 1 | React/CSS | Retro browser frame with back/forward/refresh/home and tabs. | Navigation updates page and history. | Frame 1: page A → Frame 2: loading indicator → Frame 3: page B. | Core | Complete | 22 files, e.g. toolbar/back.svg | see manifest.json | Contact sheet review + asset loads without errors in app
51 | Browser | Address bar and security indicator | 1 | React/CSS | White URL field with protocol/domain and small status icon. | URL changes on internal navigation; no external browsing. | Frame 1: old URL → Frame 2: loading → Frame 3: new URL and status. | Core | Complete | 22 files, e.g. toolbar/back.svg | see manifest.json | Contact sheet review + asset loads without errors in app
52 | Browser | Tab strip | 1 | React/CSS | Compact gray tabs with favicons and close buttons. | Tab selection switches simulated page. | Frame 1: tab A active → Frame 2: tab B selected. | Core | Complete | 22 files, e.g. toolbar/back.svg | see manifest.json | Contact sheet review + asset loads without errors in app
53 | Browser | New tab page | 1 | HTML/CSS | Simple search field and fictional bookmarked sites. | Search or bookmark opens internal simulated page. | Frame 1: empty new tab → Frame 2: query/bookmark chosen → Frame 3: result page. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/Browser.jsx#NewTab | sweep 13
54 | Browser | University portal template | 1 | HTML/CSS | Fictional campus portal with navigation and announcements. | Buttons navigate to simulated tasks. | Frame 1: portal home → Frame 2: task selected → Frame 3: task completed. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/pages/Pages.jsx#Portal | sweep 14
55 | Browser | Cloud document template | 1 | HTML/CSS | Fictional file-sharing page with document preview. | Open/preview/download actions are simulated. | Frame 1: document list → Frame 2: preview → Frame 3: task confirmation. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/pages/Pages.jsx#Cloud | sweep 21
56 | Browser | Login page templates | 4 | HTML/CSS | Fictional login pages with varied branding and layouts. | Form submit is intercepted; never stores real passwords. | Frame 1: form → Frame 2: simulated submit → Frame 3: safe training feedback. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/pages/Pages.jsx#Login x5 | sweep 15, 16
57 | Browser | Payment/tracking/support/job templates | 4 | HTML/CSS | Fictional invoice, parcel tracking, IT support, and job application pages. | Forms and task buttons lead to controlled outcomes. | Frame 1: task page → Frame 2: user action → Frame 3: completion or feedback. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/pages/Pages.jsx#Payment,Tracking,Support,Job,Invoice,Bank | sweep 17-20, 22
58 | Browser | Browser error/warning pages | 3 | HTML/CSS | Classic unavailable, blocked, and simulated warning pages. | Page displays after a controlled scenario event. | Frame 1: requested page → Frame 2: simulated block/error → Frame 3: explanation. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/pages/Pages.jsx#ErrorPage,Warning,Blocked | sweep 16, 23, 24
59 | Browser | Download dialog/manager | 1 | React/CSS | File details, source, progress, and status. | Progress moves; safe simulation ends complete or blocked. | Frame 1: ready → Frame 2: 25/60/100% → Frame 3: complete or blocked. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/Downloads.jsx | sweep 09; mail attach flow
60 | Link Inspector | Link Inspector window | 1 | React/CSS | Technical gray window with URL field and analysis tabs. | Analyze button reveals evidence progressively. | Frame 1: URL entered → Frame 2: analyzing → Frame 3: evidence displayed. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/LinkInspector.jsx | flow 12
61 | Link Inspector | URL/domain breakdown | 1 | React/CSS | Protocol, hostname, registrable domain, path, and parameters shown separately. | Domain parts highlight on hover/selection. | Frame 1: full URL → Frame 2: parts highlighted → Frame 3: explanation. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/LinkInspector.jsx | flow 12
62 | Link Inspector | Redirect chain visualization | 1 | SVG/React | Connected boxes representing simulated redirect destinations. | Nodes appear one at a time. | Frame 1: first node → Frame 2: arrows and next node → Frame 3: full chain. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/LinkInspector.jsx#Chain | flow 13 (after width fix)
63 | Link Inspector | Certificate details dialog | 1 | React/CSS | Classic properties dialog with fictional certificate details. | Tabs switch between details. | Frame 1: summary tab → Frame 2: details tab. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/LinkInspector.jsx | flow 15-cert (captured, dialog opens)
64 | Link Inspector | Reputation/evidence indicators | 6 | SVG/CSS | Known, suspicious, unknown, mismatch, and clue indicators. | Evidence appears when the player inspects the relevant item. | Frame 1: unknown → Frame 2: analysis result → Frame 3: settled status. | Core | Complete | 12 files, e.g. investigation/evidence-known.svg | see manifest.json | Contact sheet review + asset loads without errors in app
65 | Link Inspector | Investigation notes/checklist | 1 | React/CSS | Checkboxes and text area for evidence notes. | Checked clues persist during the session. | Frame 1: unchecked → Frame 2: checked → Frame 3: summary includes clue. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/LinkInspector.jsx | flow 14-notes
66 | Security Center | Security Center dashboard | 1 | React/CSS | Incident list and report controls in classic desktop style. | New reports appear in history. | Frame 1: dashboard → Frame 2: report submitted → Frame 3: history updated. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/SecurityCenter.jsx | sweep 12
67 | Security Center | Report form | 1 | React/CSS | Threat category, evidence checklist, and notes fields. | Validation highlights missing required fields. | Frame 1: blank → Frame 2: completed → Frame 3: validation/submission. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/SecurityCenter.jsx | flow 16
68 | Security Center | Threat category icons | 8 | SVG/PNG | Credential theft, impersonation, malicious link, attachment, payment fraud, social engineering, other. | Selected icon gets a border/highlight. | Frame 1: neutral options → Frame 2: selected category. | Core | Complete | 16 files, e.g. security/threat-credential.svg | see manifest.json | Contact sheet review + asset loads without errors in app
69 | Security Center | Report submission feedback | 3 | React/CSS | Submitted, incomplete, and rejected dialogs. | Dialog appears after submission attempt. | Frame 1: submit → Frame 2: progress → Frame 3: outcome dialog. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/SecurityCenter.jsx | flow report submitted dialog
70 | Security Center | Incident history and status badges | 1 | React/CSS | Rows with incident ID and status. | Status changes based on scenario resolution. | Frame 1: submitted → Frame 2: under review → Frame 3: resolved. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/SecurityCenter.jsx | flow 18
71 | Security Center | Investigation debrief | 1 | React/CSS | Summary of decision, relevant evidence, and lesson. | Sections reveal after resolution; XP count animates. | Frame 1: decision → Frame 2: evidence summary → Frame 3: XP reward. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/Debrief.jsx | flow 19
72 | Files | File Manager window | 1 | React/CSS | Folder tree, file list, and details view. | Folder selection updates file list. | Frame 1: folder A → Frame 2: folder B selected → Frame 3: contents update. | Later | Complete | No file (CSS / React component) | src/cyberdesk/apps/Files.jsx | sweep 06
73 | Files | File type icons | 12 | SVG/PNG | Folder, text, PDF, image, spreadsheet, archive, executable, script, unknown, shortcut, attachment, quarantined. | Selected and quarantined states use overlays. | Frame 1: normal → Frame 2: selected → Frame 3: warning/quarantine. | Later | Complete | 38 files, e.g. icons/filetype/folder.svg | see manifest.json | Contact sheet review + asset loads without errors in app
74 | Files | File properties dialog | 1 | React/CSS | Filename, extension, size, source, and metadata. | Tabs or sections switch between details. | Frame 1: general → Frame 2: details. | Later | Complete | No file (CSS / React component) | src/cyberdesk/apps/Files.jsx | sweep2 s2-01
75 | Files | Document viewer/text editor | 2 | React/CSS | Harmless simulated document and monospaced editor. | Open and close; optional typing only in editor. | Frame 1: file icon → Frame 2: viewer opens → Frame 3: content displayed. | Later | Complete | No file (CSS / React component) | src/cyberdesk/apps/Notes.jsx | sweep 07; sweep2 s2-02
76 | Files | Download manager | 1 | React/CSS | File rows and progress bars. | Progress increments through safe simulated states. | Frame 1: queued → Frame 2: downloading → Frame 3: complete/blocked. | Later | Complete | No file (CSS / React component) | src/cyberdesk/apps/Downloads.jsx | sweep 09
77 | Files | Quarantine/unknown-file dialogs | 2 | React/CSS | Warning dialog with file details and safe actions. | Dialog opens after simulated risky action. | Frame 1: file selected → Frame 2: warning appears → Frame 3: quarantine/cancel. | Later | Complete | No file (CSS / React component) | src/cyberdesk/apps/Files.jsx | sweep2 s2-03, s2-05
78 | Progression & Extras | System notification family | 10 | React/CSS | New email, security alert, download, network, update, XP, achievement, task completion, evidence, error. | Slide in, remain briefly, dismiss or fade out. | Frame 1: hidden → Frame 2: slide in → Frame 3: visible → Frame 4: dismiss. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/Notifications.jsx | all screenshots (toasts)
79 | Progression & Extras | XP counter and progress bar | 2 | React/CSS | Pixel-style numeric counter and horizontal progress bar. | Counter increments; bar fills to new value. | Frame 1: old XP → Frame 2: count ticks upward → Frame 3: new XP. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/Notifications.jsx#XpCounter,XpMini | sweep2 s2-12, tray
80 | Progression & Extras | Rank badges | 8 | SVG/PNG | Pixel emblems with consistent border and palette. | Optional glow when rank is unlocked. | Frame 1: locked/gray → Frame 2: unlock flash → Frame 3: full-color badge. | Later | Complete | 33 files, e.g. progression/ranks/trainee.svg | see manifest.json | Contact sheet review + asset loads without errors in app
81 | Progression & Extras | Achievement icons | 16 | SVG/PNG | Trophies, stars, shields, investigation symbols. | Unlock notification appears; icon briefly scales up. | Frame 1: locked → Frame 2: unlock flash → Frame 3: unlocked. | Later | Complete | 65 files, e.g. progression/achievements/first_report.svg | see manifest.json | Contact sheet review + asset loads without errors in app
82 | Progression & Extras | Mission assignment card | 1 | React/CSS | Classic framed task panel with objectives. | Slides in at mission start. | Frame 1: hidden → Frame 2: slide in → Frame 3: objective list. | Core | Complete | No file (CSS / React component) | src/cyberdesk/os/Desktop.jsx#MissionCard | sweep 04
83 | Progression & Extras | Session summary | 1 | React/CSS | Report with decisions, evidence, XP, and lessons. | Values appear in sequence. | Frame 1: title → Frame 2: metrics → Frame 3: debrief complete. | Core | Complete | No file (CSS / React component) | src/cyberdesk/apps/Debrief.jsx#Summary | sweep2 s2-14
84 | Progression & Extras | CRT monitor sprite | 2 | PNG/SVG | Beige monitor with dark glass and pixel glow. | Optional screen glow pulse. | Frame 1: screen off → Frame 2: screen on → Frame 3: glow settles. | Later | Complete | 4 files, e.g. sprites/crt-off.svg | see manifest.json | Contact sheet review + asset loads without errors in app
85 | Progression & Extras | Computer tower/keyboard/mouse | 3 | PNG/SVG | Classic beige hardware with crisp pixel edges. | Static decorative objects. | Frame 1: static sprite; optional tiny power LED switches on. | Later | Complete | 8 files, e.g. sprites/tower.svg | see manifest.json | Contact sheet review + asset loads without errors in app
86 | Progression & Extras | Floppy disks/CDs/USB drives | 12 | PNG/SVG | Small storage-device sprites. | Static; may move as part of a scripted scene. | Frame 1: object at rest → Frame 2: slight movement/selection. | Later | Complete | 24 files, e.g. sprites/storage/floppy-blue.svg | see manifest.json | Contact sheet review + asset loads without errors in app
87 | Progression & Extras | Office hardware/props | 10 | PNG/SVG | Printer, telephone, desk lamp, papers, cables, and folders. | Optional printer paper movement or lamp glow. | Frame 1: idle → Frame 2: one simple moving part → Frame 3: idle. | Later | Complete | 24 files, e.g. sprites/office/printer.svg | see manifest.json | Contact sheet review + asset loads without errors in app
88 | Progression & Extras | Pixel security mascot/portraits | 6 | PNG sprite sheet | Small character portraits or security mascot in one consistent pixel style. | Idle blink, subtle bob, or reaction frame. | Frame 1: idle → Frame 2: blink/reaction → Frame 3: idle. | Later | Complete | 15 files, e.g. mascot/finn-idle.svg | see manifest.json | Contact sheet review + asset loads without errors in app
89 | Progression & Extras | Primary UI font | 1 | Font file/CSS | Legible classic desktop-style sans-serif. | No animation. | Static typography asset. | Core | Complete | 4 files, e.g. fonts/pixelify-sans-latin-400-normal.woff2 | see manifest.json | Contact sheet review + asset loads without errors in app
90 | Progression & Extras | Monospace terminal font | 1 | Font file/CSS | Readable monospaced font for logs and URLs. | No animation. | Static typography asset. | Core | Complete | 4 files, e.g. fonts/vt323-latin-400-normal.woff2 | see manifest.json | Contact sheet review + asset loads without errors in app
91 | Progression & Extras | Optional bitmap display font | 1 | Font file/CSS | Pixel font for short headings and logo text. | No animation. | Static typography asset. | Later | Complete | 4 files, e.g. fonts/press-start-2p-latin-400-normal.woff2 | see manifest.json | Contact sheet review + asset loads without errors in app
92 | Progression & Extras | Audio effects library | 20 | WAV/OGG | Startup, shutdown, clicks, warning, email, typing, evidence, report, XP, achievement, ambience. | Play short clips on the corresponding event; allow mute. | Not frame-based; define trigger, duration, volume, and mute behavior. | Later | Complete | 40 files, e.g. audio/startup.ogg | see manifest.json | Contact sheet review + asset loads without errors in app NOTE: clips decode, load (HTTP 200) and play without errors; audible quality/mix not yet human-reviewed.
93 | Progression & Extras | Accessibility states | 1 | React/CSS | Focus outlines, high contrast, reduced motion, touch alternatives. | Motion reduced or disabled based on user preference. | Frame 1: normal state → Frame 2: accessible alternative state. | Core | Complete | No file (CSS / React component) | src/cyberdesk/styles/os.css; src/cyberdesk/CyberDesk.jsx (data-motion/contrast/touch) | sweep2 s2-10, s2-11
94 | Progression & Extras | About/settings/help utilities | 4 | React/CSS | About, system properties, display/sound settings, help/log viewer. | Dialogs open, tabs switch, controls update. | Frame 1: app icon → Frame 2: utility window → Frame 3: selected setting/log. | Later | Complete | No file (CSS / React component) | src/cyberdesk/apps/Utilities.jsx | sweep 10; sweep2 s2-07..13

## Animation Notes
No. | Asset / Component | Animation Trigger | Frame / State Sequence | Implementation Hint | Implemented in | Status
1 | CyberDesk logo | Boot starts | Screen dark → screen lights → logo appears → slight glow settles | CSS opacity/brightness; SVG or PNG logo. | BootScreen logo frames; anim.css cd-logo | Complete
2 | Startup diagnostics | Boot timeline | Cursor → line 1 → line 2 → checks complete | Render text as text; stagger with CSS or controlled React state. | BootScreen diagnostics (timed lines) | Complete
3 | Loading bar | Boot progress | 0% → 25% → 60% → 100% | CSS width transition; respect reduced-motion. | ProgressBar segments; Boot.jsx | Complete
4 | Desktop reveal | Boot completes | Black → wallpaper fades in → icons/taskbar appear | Opacity/transform transitions; no page reload. | Boot.jsx phase change + desktop fade/scale | Complete
5 | Window opening | App icon activated | Icon selected → window scales/fades in → focused title bar | Shared AppWindow animation. | AppWindow anim-open (cd-win-open) | Complete
6 | Window minimizing | Minimize button | Window shrinks/fades toward taskbar → taskbar indicator remains | CSS transform/opacity; keep app state mounted. | AppWindow anim-minimize toward taskbar | Complete
7 | Window maximizing | Maximize button | Window expands to viewport work area | Animate geometry or use CSS transition. | AppWindow geoAnim transition | Complete
8 | Window focus | Window clicked | Inactive title bar → active blue title bar; z-index increases | Window manager updates focused ID. | .win.active/.inactive title colours | Complete
9 | Desktop icon | Click/double-click | Normal → hover/selected → application opens | Use pointer and keyboard accessible activation. | .dicon hover/sel/dblclick states | Complete
10 | New email | Scenario event | Notification hidden → slide in → visible → dismiss/fade | Queue notifications and support manual dismissal. | store arrival timers -> Toasts + row slide-in | Complete
11 | Unread email | Email opened | Bold row/unread icon → read style | Update message state, not just its appearance. | Mail unread->read row state | Complete
12 | URL hover preview | Pointer enters link | No URL → actual destination shown in status bar | Use the exact simulated href; do not navigate. | Mail link hover -> status bar + preview tip | Complete
13 | Link Inspector | Analyze action | URL entered → progress → domain breakdown → evidence | Derive from scenario data; avoid unsupported live scan claims. | LinkInspector staged progress + verdict reveal | Complete
14 | Redirect chain | Inspect redirects | Node 1 → arrow/node 2 → complete simulated chain | Render a sequence of connected nodes. | LinkInspector#Chain staged reveal | Complete
15 | Report submission | Submit report | Button pressed → progress → confirmation or validation error | Score once; make submission idempotent. | SecurityCenter submit -> status progression | Complete
16 | Evidence discovered | Evidence action | Neutral icon → highlighted clue → saved evidence state | Persist evidence in central investigation state. | Evidence toast + clue highlight | Complete
17 | XP counter | Scenario resolved | Old total → brief increment → new total | Reward through one scoring engine. | useCountUp XpCounter + progress bar fill | Complete
18 | Achievement unlock | Threshold reached | Locked/gray → short flash → unlocked badge | Trigger only when criterion is actually met. | Achievement toast + sparkle | Complete
19 | Download progress | Download requested | Queued → 25% → 60% → 100% → complete/blocked | Simulated progress; no real executable download. | Downloads progress bar states | Complete
20 | CRT scanlines | Desktop displayed | Static scanlines → subtle vertical drift → loop | Optional CSS overlay; disable for reduced motion. | CrtOverlay scanlines (Settings toggle) | Complete
21 | Cursor busy | Long simulated operation | Arrow → busy cursor → arrow | Use sparingly; never block input unnecessarily. | busy.js useBusyCursor -> .cyberdesk.busy cd-busy-cursor (verified: class set/cleared in e2e) | Complete
22 | Shutdown | Exit confirmed | Desktop dims → shutdown message → black | Return to hub after confirmation; save progress first. | ShutdownScreen sequence + audio | Complete